## Sheet1
Issue | Owner | Criticality(High/Med/Low)
Update button on Network Screen | Vivek | Medium | Resolved
Update button on Enterprise Screen | Vivek | Medium | Resolved
Update button on Enterprise Admin Screen | Vivek | Medium | Resolved
Update button on Organization Screen | Vivek | Medium | Resolved
Update button on Organization Admin Screen | Vivek | Medium | Out of scope
Update button on Employee Screen | Vivek | Medium | Out of scope
Delete button on Network Screen | Vivek | Medium | Resolved
Delete button on Enterprise Screen | Vivek | Medium | Resolved
Delete button on Enterprise Admin Screen | Vivek | Medium | Resolved
Delete button on Organization Screen | Vivek | Medium | Resolved
Delete button on Organization Admin Screen | Vivek | Medium | Out of scope
Delete button Organization Admin Screen | Vivek | Medium | Out of scope
Delete button on Employee Screen | Vivek | Medium | Out of scope
Assign to me button should be disabled after send to legal | Raj | Medium | Resolved
Drug name validation in table where it is added/updated | Tej | Medium | No need to implement
On check inventory button on supplier screeen null pointer exception | Raj | High | Resolved
Back button chemist coworker screen | Raj | Medium | Resolved
Inventory duplicate drugs gets created | Tej | Medium | Resolved
Issue on Assign to Supplier screen. After submit user should not be allowed to submit again | Raj | Medium | Resolved
Back button on Assign to screens to be correctly coded | Vivek | High | Done
Stack push and pop remaining for Manufacturer flow | Vivek | High | Done
Define different states of the Work Request | All | High | Done
delete button on update order | Tej | High | Resolved | Delete button removed
add rows and then unfilled and save error | Tej | High | Resolved
back button remove from card layout the screen. NO BACK BUTTON ISSUES | Tej | High | Same as 48
send to supplier assign to me shouldnt be enable | Raj | Medium | Done
Sender Receiver on all screen | All | High | Done. Raj Tej Please check once
Reject button disable after send to supplier | Raj | High | Done
Remove manager column from worker table | Tej | High | Done
View screen table disable | Tej | High | Done
Add in inventory once request is send from supplier to chemist | Raj | High | Done
Add in inventory once request id send from manu to supplier | VIvek | High | Done
only after Legal check request bid allow | Raj | Medium | Done
Remove legal approved or reject from all legal entities + producers | Vivek | High | Done
Alert after chemist order is fulfilled | Vivek | Medium | Done for success scenario
delete inventory in producer | Tej |  | Done
Enabled Request column in Request Bid screen | Raj | High | Resolved
Delete rejected request from worker end | Tej | Medium | Done, Removed the delete button
Remove Transport, Supplier coordinator | Vivek | Medium | Done
Order Completed in Worker Screen can also be editrd | Raj | High | resolved
Duplicate drugs in order and update screen | Tej | High | Done
Cancel button disable | Vivek | High | Done
Logout should be allowed on WorkAreaScreen | Tej | Medium | Doing code was already inplemented need discussion
Analysis | Tej | Medium | Done
Multithreading | Vivek | High | Done
UUID
Stream | Raj | Medium | Done
Log4j2 asynchronus | Vivek | Low | Out of scope
Across Network work request | All | High | Done
Filter completed orders on Chemist screen | Tej | Medium | Done
dulicate drugs in list ignorcase | Tej | High | Done
add org table user acct screen | Vivek |  | Done
view and update order details screen add row (UI ISssue) | Tej | High | Done
If status send to supplier worker can't again send request for approval | Tej | High | Done
Change roletype for Producer from PROD to PRODUCER | Vivek | Medium | Done
Change error message on Organization delete button | Vivek | High | Done
Quantity not updating in supplier inventory for new drugs | Vivek | High | Done
Approve button should be disbaled after status is Approved | Tej | High | Done
Manager work area Status "Send to manufacturer " send to supplier is enable | Tej | High | Done
Manager work area Status "Send to manufacturer " on click approve shows wrg msg